# Scanned Book Reader: 6-Week Product + Engineering Roadmap

Prepared: 2026-02-06

Roadmap basis: Current repo capabilities, documented TODOs, and architecture constraints observed in frontend hooks, backend routes, and config defaults.

## Current Baseline (From Repository)

Core reader features are implemented: navigation, zoom/rotate/fit, OCR modal, bookmarks, TOC, audio, streaming audio, and print-to-PDF.

Ingestion paths are present for scanned PDFs and text/chapter workflows, including chapter narration and audio generation jobs.

Data model is file-based under /data with no database layer (book folders, page OCR text, audio files, bookmarks.txt, toc.json).

Several capabilities remain in TODO.md: bookmark filtering, AI transforms (summary/flashcards/translation/story), OCR-all-pages flow, and speech-to-text.

Quality assurance is manual smoke testing only; no automated test suite is currently configured.

## Architecture Constraints to Plan Around

External dependency requirements: pdftoppm for PDF import, and stream server availability for websocket TTS streaming.

Configuration sensitivity: OCR/TTS/stream rely on environment variables and provider-specific settings.

Current stream fallback host includes myserver.home defaults in client/server code paths, creating deployment portability risk.

Print API currently limits generated PDFs to 10 pages and only supports PNG/JPEG page sources.

All path handling is filesystem-safe and strict; new features must preserve existing path/book validation rules.

## Milestones

M1 (End Week 2): Stable platform baseline and environment-safe configuration.

M2 (End Week 4): High-impact workflow expansion delivered (bookmark filtering + AI utilities v1).

M3 (End Week 6): Release-ready quality bar with automated checks, runbooks, and risk controls.

## Week-by-Week Plan

| Week | Weekly Goal | Deliverables | Dependencies | Risks (and Mitigation) |
| --- | --- | --- | --- | --- |
| Week 1 | Plan lock and baseline hardening | - Produce architecture map (frontend hooks <-> API routes <-> /data files). - Freeze scope for 6-week delivery with acceptance criteria. - Align env contract for OCR/TTS/stream across dev and prod. | - Access to existing deployment env vars. - Maintainer sign-off on scope priorities. | - Scope churn risk; mitigate with written acceptance criteria and change-control gate. |
| Week 2 | Reliability and config cleanup | - Remove hardcoded stream host assumptions and centralize env-driven endpoints. - Improve API error consistency for OCR/audio/TOC flows. - Create reusable smoke-test checklist script for critical paths. | - Available stream/OCR backends for testing. - Agreement on shared error response format. | - Regression risk in audio/streaming hooks; mitigate with mandatory smoke pass per merge. |
| Week 3 | Bookmark and OCR throughput features | - Implement bookmark filter mode (show bookmarked pages only). - Expand batch OCR to support full-book runs with pause/resume/retry clarity. - Add persistent progress feedback for long OCR jobs. | - Stable manifest ordering and OCR endpoint performance. - UI state persistence decisions. | - Long-running OCR jobs may fail intermittently; mitigate with resumable queue state and explicit failure summaries. |
| Week 4 | AI utility layer v1 | - Ship first content transforms: page summary, translation, flashcard generation. - Save generated artifacts with deterministic filenames per page/chapter. - Add minimal UI actions from text/audio views. | - Prompt tuning time. - API keys/model quotas and latency budget. | - Output quality variance; mitigate via constrained prompts, editable outputs, and manual approve/save step. |
| Week 5 | Speech and domain-specific additions | - Add speech-to-text ingestion flow (upload/transcribe/store). - Implement recipe-oriented helpers (shopping list, recipe sanity checks) for relevant books. - Add feature flags for optional AI tools (story rewrite/diagram generation deferred or experimental). | - STT provider selection and supported file formats. - Product decisions on where transcriptions are stored. | - Feature sprawl risk; mitigate with strict v1 boundaries and disabled-by-default experimental flags. |
| Week 6 | Release readiness and operational quality | - Add CI checks (type-check + targeted API/unit tests). - Finalize deployment/runbook docs for binaries, env vars, and fallback behavior. - Execute regression pass and produce release candidate + rollback notes. | - CI runner access and sample fixtures/books for tests. - Maintainer time reserved for final bug triage. | - Late integration defects; mitigate by scheduling stabilization buffer and freeze window before release. |

## Dependency Callouts

Runtime services: OCR backend (openai/llmproxy/openai_compat), TTS provider, websocket stream server.

System binaries: pdftoppm required for PDF upload; ffprobe availability improves chapter audio metadata.

Infrastructure: secure environment variable management and parity between local/staging/production.

Data compatibility: preserve current /data folder format to avoid migration breakage for existing books.

## Risk Register

Service dependency risk: external OCR/TTS/stream outages can block primary user flows.

Scalability risk: large books increase OCR/audio batch duration and failure exposure.

Quality risk: AI-generated text may require human review to maintain trust and usefulness.

Testing risk: manual-only QA can miss regressions across tightly coupled components/hooks.

Operations risk: implicit defaults and environment drift can cause non-reproducible behavior.